## Pilot tracker
SHIDA Restaurants & Malewa — implementation tracker
As of | 2026-10-11 16:26 |  | Core target | 2026-10-10 18:00 | Original 18-item target; Stockholm time
Core pilot items 01–18 and founder-requested extras 19–21 are implemented locally; release checks and deployment remain separate.
Needed | 21 |  | Done | 21 |  | Open | 0
Hours | 0 |  | State | Expanded scope implemented
Expanded implementation complete; release checks remain.
Release checks remain: no final green Backend full run through 0148; live PostgreSQL reservations, device/WhatsApp acceptance and deployment pending.
ID | Deliverable | Repository | In scope? | Status | Depends on | Next action / limit | Evidence | Updated
01 | Public restaurant page, menu and general QR | Backend + both frontends | Yes | Implemented | — | Maintain existing Free access | S1 | 2026-10-10
02 | Guest private visits and repeat rounds | Backend | Yes | Implemented | 01 | Preserve separate immutable orders | S2 | 2026-10-10
03 | Guest QR ordering page and pickup proof | NIHILOBA | Yes | Implemented | 02 | Keep private cookie and ready-only code | S3 | 2026-10-10
04 | Owner POS, Kitchen and numerical stock | Backend + both frontends | Yes | Implemented | 01 | Retain immediate counter sale path | S4, S11, S12 | 2026-10-10
05 | Assigned Kitchen for customer orders | Backend + Business | Yes | Implemented | 04 | Assisted orders now covered by 10B3 | S5, S15 | 2026-10-10
06 | Prepared assisted order foundation | Backend | Yes | Implemented | 04 | Use accepted-to-ready lifecycle | S6 | 2026-10-10
07 | Service grants, groups and guest consent API | Backend | Yes | Implemented | 06 | Keep grants exact to establishment | S7 | 2026-10-10
08 | Waiter Service screen and guest approval | Business + NIHILOBA | Yes | Implemented | 07 | Checkout now integrated in 10F3 | S8, S10, S23, S24 | 2026-10-10
09 | 10B3 Kitchen + Bar routing and worker APIs | Backend | Yes | Implemented | 06, 07 | 0141 is in current 0145 migration lineage | S15, S18, S25 | 2026-10-10
10 | 10F2 Kitchen + Bar staff screens | Business + NIHILOBA | Yes | Implemented | 09 | Revalidate with 0145 Backend before rollout | S16, S17, S25 | 2026-10-10
11 | 10B4 delegated stock operations | Backend | Yes | Implemented | 04 | 0142 is in current 0145 migration lineage | S18, S19, S25 | 2026-10-10
12 | 10B4 staff Stock screen | Business | Yes | Implemented | 11 | Coordinate rollout with 0145 Backend | S19, S25 | 2026-10-10
13 | 10B5a payment methods and money records | Backend | Yes | Implemented | 07 | Used by 10F3 Service checkout | S20, S21, S23, S24 | 2026-10-10
14 | 10B5b payment receipt and recovery APIs | Backend | Yes | Implemented | 13 | Used by Service checkout and private guest summary | S21, S23, S24 | 2026-10-10
15 | 10F3 checkout in the same Service screen | Business + NIHILOBA | Yes | Implemented | 14 | Release-environment mixed-currency, refund, stale-write and phone acceptance remains | S23, S24 | 2026-10-10
16 | 10B6a expenses and cash movements | Backend | Yes | Implemented | 13 | Journal feeds implemented 10B6b daily close | S22, S25 | 2026-10-10
17 | 10B6b daily closing and reports | Backend | Yes | Implemented | 14, 16 | Final close after local midnight; 0145 sole head; release acceptance remains | S25 | 2026-10-11
18 | 10F4 owner daily operations screen | Business + NIHILOBA | Yes | Implemented | 17 | Owner screens integrated with real Backend; device/live acceptance remains | S26, S27 | 2026-10-11
19 | Optional guest QR auto-accept setting | Backend + both frontends | Yes | Implemented | 03 | 0146; off by default; final broad Backend suite and live acceptance remain | S29 | 2026-10-11
20 | Fixed tables and table-specific QR | Backend + frontends | Yes | Implemented | 03, 19 | 0147; paid Business only; full Backend suite and physical table acceptance remain | S30 | 2026-10-11
21 | Reservations | Backend + frontends | Yes | Implemented | 01 | 0148; Free and account-based; live PostgreSQL/WhatsApp acceptance remains | S31 | 2026-10-11
22 | Multi-location reporting | Business | No | Deferred | 17 | Later Organization scope | S9 | 2026-10-10
23 | Ingredient recipes and costing | Backend + frontends | No | Deferred | 11 | Requires exact unit and recipe policy | S9 | 2026-10-10
24 | Alcoholic-drink policy for Nganda | Product decision | No | Needs decision | 09 | Current restaurant ordering supports non-alcoholic drinks | S9 | 2026-10-10
25 | Physical-device and human language acceptance | All products | No | Excluded | 18 | Outside implementation-only milestone | S3 | 2026-10-10
26 | Live rollout and production acceptance | All products | No | Excluded | 18 | Outside implementation-only milestone | S3 | 2026-10-10
27 | Inherited full-suite failures | Backend + both frontends | No | Deferred | — | No final green Backend full run through 0148: 0146 snapshot pre-final, 0147 stopped, 0148 stopped. Frontend baselines remain. | S29, S30, S31 | 2026-10-11
28 | Guest proxy rate-limit capacity review | Backend + NIHILOBA | No | Deferred | 03 | Needed before production traffic | S3 | 2026-10-10

## Roadmap
Restaurant & Malewa — full roadmap aligned to the pilot
Original statuses are retained. All 21 scoped implementation items are complete locally; Backend sole head is 0148. Release gates remain open.
The implementation target is separate from device tests, live acceptance and deployment. Fixed tables, reservations and multi-location reporting follow later.
ID | Original milestone | Original status | Current status | What is implemented now | Remaining work / boundary | Pilot IDs | Phase | Evidence
R0 | Business / foundation readiness | Implemented / ready | Implemented | Organization and Personal ownership, paid access and Business/public foundations. | Maintain exact access and entitlement checks. | 01–08 | Foundation | S1, S13
R1 | Public Restaurant & Malewa marketplace | Implemented | Implemented locally | Profiles, public menus, prices, discovery and permanent QR entry. | Live marketplace acceptance remains a release task. | 01 | Foundation | S1, S13
R2 | Menu & Malewa food model | Partial / verify | Partial / verify | Public menus and guest ordering are working locally. | Verify composed plates, pricing and WhatsApp plate flow against the original scope. | 01, 03 | Verify after pilot | S1, S3, S13
R3 | Customer ordering | Implemented | Implemented locally | Customer orders, private guest visits, repeat rounds, pickup proof and receipts. | Live channel and device acceptance remains open. | 02, 03 | Foundation | S2, S3, S13
R4 | Basic Restaurant operations | Implemented / partial | Core pilot implemented | Owner POS, Service checkout, Kitchen/Bar, Stock, expense/cash and daily closing screens are implemented. | Resolve release gates and complete a controlled working-day acceptance. | 04–18 | Pilot implementation | S4–S9, S13, S15–S27
R5 | Basic analytics | Implemented | Basic implemented | Basic sales/order figures and daily money/expense closing reports exist. | Advanced trends and margins remain later scope. | 17, 18 | Pilot + later | S1, S9, S13, S25–S27
R6 | Cross-surface adoption | Implemented | Core pilot integrated | Core flows, Kitchen/Bar, Business Stock, Service checkout and owner daily screens are integrated. | Physical-device and live-establishment acceptance remains. | 03, 05, 08, 10, 12, 15, 18 | Pilot implementation | S3, S8, S9, S13, S16–S19, S23–S27
R7 | Real-world acceptance / release closure | Open | Open — after implementation | Focused checks and real-Backend browser flows exist for completed batches. | Complete Backend broad-suite triage, live PostgreSQL 0148, physical devices, WhatsApp, deployment and monitoring. | 25–28 | Release gate | S3, S13, S25–S31
R8 | Paid Restaurant management V1 | Not started | Core pilot implemented | Owner POS, assigned Kitchen/Bar, waiter checkout, staff Stock and daily money screens are implemented. | Release acceptance and inherited test-gate triage remain. | 04–18 | Pilot implementation | S4–S9, S13, S15–S27
R9 | Advanced Restaurant management | Later | Requested extras implemented | Auto-accept, optional fixed-table QR and simple reservations are implemented locally. | Advanced capacity, recipes, multi-location, shifts and split bills remain later; release acceptance is open. | 19–23 | Extra + later | S9, S13, S28–S31
R10 | Growth & CRM | Later | Later | No approved implementation claimed. | Favorites, promotions, loyalty and customer campaigns. | — | Later | S13
Added implementation and release work
Order | Work | Pilot IDs | Boundary
1 | Triage Backend and frontend suite gates | 27 | Final complete run against sole 0148; classify failures
2 | Rehearse 0148 on live PostgreSQL staging | 21 | Reservation migration did not run on live server
3 | Physical stock, table and money acceptance | 19, 20, 25 | Controlled one-establishment working day
4 | Live WhatsApp reservation acceptance | 21, 26 | Four languages, provider failures and recovery
5 | TLS, proxy, retention and rollout acceptance | 26, 28 | After implementation and release checks
6 | Recipes and multi-location reporting | 22, 23 | Later scope
7 | Advanced management and growth | R9–R10 | Later scope

## Batch log
Completed batch log
Append one row after each completed handoff. Then update the matching Pilot tracker status, date, action and evidence reference.
Batch | Implemented deliverable | Repository | Result / limit | Evidence | Recorded
07B | Owner Kitchen | Backend + frontends | Implemented locally; owner access. | S12 | 2026-10-10
07C | Owner POS and counter preferences | Backend + frontends | Implemented locally; payment unverified. | S4 | 2026-10-10
08B2 | Assigned worker Kitchen | Backend + Business | Implemented locally; inherited release failures open. | S5 | 2026-10-10
09B1 | Private guest visits and repeat rounds | Backend | Implemented locally; migration 0138. | S2 | 2026-10-10
09B2 | Guest QR ordering interface | NIHILOBA | Implemented locally; device/live acceptance open. | S3 | 2026-10-10
10B1 | Prepared assisted orders | Backend | Implemented locally; migration 0139. | S6 | 2026-10-10
10B2 | Service grants, groups, guest consent | Backend | Implemented locally; migration 0140. | S7 | 2026-10-10
10F1 | Waiter Service screen and guest approval | Business + NIHILOBA | Implemented locally; staffed pilot incomplete. | S8, S10 | 2026-10-10
10B3 | Kitchen/Bar routing, station progress and recovery | Backend | Implemented locally; migration 0141; screens delivered in 10F2. | S15 | 2026-10-10
10F2 | Kitchen/Bar staff screens and owner controls | Business + NIHILOBA | Implemented locally; 0142 rollout lineage needs reconciliation. | S16, S17 | 2026-10-10
10B4 | Delegated stock and manual ingredient use | Backend | Implemented locally; migration 0142; Business screen delivered. | S18 | 2026-10-10
10B4 Stock | Assigned stock worker and admin controls | Business | Implemented locally; B4 API compatible with sole 0143 head. | S19 | 2026-10-10
10B5a | Declared money and group checkout foundation | Backend | Implemented locally; sole head 0143; B5b added protected receipt. | S20 | 2026-10-10
10B5b | Protected receipt, guest summary and money recovery | Backend | Implemented locally; 0143 unchanged; Service checkout delivered in 10F3. | S21 | 2026-10-10
10B6a | Paid expenses and cash movement foundation | Backend | Implemented locally; sole head 0144; daily close remains. | S22 | 2026-10-10
10F3 | Service checkout and private guest payment summary | Business + NIHILOBA | Implemented locally; release-environment acceptance remains. | S23, S24 | 2026-10-10
10B6b | Confirmed-zone daily closing and immutable reports | Backend | Implemented locally; sole head 0145; broad suite difference unresolved. | S25 | 2026-10-11
10F4 | Owner expense, cash and daily closing screens | Business + NIHILOBA | Implemented locally against real Backend; device/live acceptance remains. | S26, S27 | 2026-10-11
Guest QR auto-accept | Optional audited QR acceptance and controls | Backend + both frontends | Implemented locally; sole head 0146; final broad suite not rerun. | S29 | 2026-10-11
Fixed tables | Paid fixed-table QR and table delivery | Backend + both frontends | Implemented locally; sole head 0147; broad Backend run incomplete. | S30 | 2026-10-11
Reservations | Free account-based seller-confirmed booking | Backend + both frontends | Implemented locally; sole head 0148; live PostgreSQL and full suite pending. | S31 | 2026-10-11
Personal solo Settings | Saved capabilities, setup requirements, intake confirmation and recovery | Website; Backend and WhatsApp contracts unchanged | Partial: Website build, typecheck and changed-file lint pass; 132 focused unit executions pass (includes existing .s3a-local duplicates); 25 production-preview browser checks pass at 360/820/1440 px in FR/EN/LN/SW. Backend intake/reservations/WhatsApp focus: 525 passed, 2 expected Organization-only skips in 1088.19s. No Backend or WhatsApp source change. Prior full-suite failures remain separate; no full-suite rerun. Staging, real WhatsApp phone/provider, physical devices and human language acceptance remain open. | S32 | 2026-10-15
Receiving orders | Status, setup reasons, dated pickup/delivery and safe review | Website + minimal Backend/WhatsApp | Build/typecheck/changed-file lint pass. Website: 116 unit executions, 52 production-browser cases across FR/EN/LN/SW at 360/820/1440. Backend: 246 + 7 pass, fresh SQLite; head 0163, no migration. Six older combined C1-E cases fail on obsolete activity/amount expectations; full-suite red gates not rerun. Staging, real WhatsApp phone, physical devices, human language and reusable-schedule acceptance remain open. No deploy or production change. | S33 | 2026-10-15

## Evidence
Evidence and status definitions
Statuses use the latest completed handoff report available at the checkpoint. Planned means no completion report was found.
Update this workbook after each batch handoff: mark the item in Pilot tracker, append the batch in Batch log, and cite the new report here.
ID | Evidence path | Supports
S1 | C:\NIHILOBA\Backend\docs\business_modules\restaurants_malewa.md | Canonical Restaurant scope and Free baseline
S2 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_09b1_guest_visits.md | Guest Backend visits, rounds and sole head 0138 at 09B1
S3 | C:\NIHILOBA\nihiloba-website\docs\restaurants-rm-v11-09b2.md | Guest page, proxy, device/live limits and rate-limit risk
S4 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_07c.md | Paid owner POS; owner Kitchen/inventory status in canonical spec
S5 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_08b2_assigned_kitchen.md | Assigned Kitchen worker implementation
S6 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b1_assisted_ordering.md | Prepared assisted Backend; migration 0139
S7 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b2_service_groups.md | Service worker/group Backend; migration 0140
S8 | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10f1_service_ordering.md | Business Service screen; Personal/guest counterpart also inspected
S9 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10a_single_establishment_pilot_contract.md | Remaining B3/F2/B4/B5/B6 implementation sequence and later features
S10 | C:\NIHILOBA\nihiloba-website\docs\restaurants_rm_v11_10f1_service_ordering.md | Personal Service, guest approval and inherited frontend failures
S11 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_06b.md | Numerical stock implementation
S12 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_07b.md | Owner Kitchen implementation
S13 | C:\Users\mabal\OneDrive\NIHILOBA\SHIDA\Development\SHIDA_Restaurant_Malewa_Roadmap.xlsx | Original R0–R10 roadmap and historical statuses
S14 | C:\Users\mabal\OneDrive\NIHILOBA\SHIDA\Development\shida_restaurants_pilot_tracker_2026-10-10.xlsx | Earlier 18-item pilot tracker; merged into this master file
S15 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b3_preparation.md | 10B3 Kitchen/Bar Backend preparation, migration 0141 and validation
S16 | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10f2_preparation.md | Business 10F2 completion, assigned Bar, routing and 0142 rollout blocker
S17 | C:\NIHILOBA\nihiloba-website\docs\restaurants_rm_v11_10f2_preparation.md | Website 10F2 completion, Personal/Free preparation and 0142 rollout blocker
S18 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b4_stock_workers.md | 10B4 completed Backend stock workers, ingredient use and migration 0142
S19 | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10b4_stock.md | Business stock screen completion and compatibility with concurrent 0143 head
S20 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b5a_money_foundation.md | 10B5a Backend bill, declared money, recovery boundary and sole head 0143
S21 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b5b_receipt_recovery.md | 10B5b protected receipt, guest money summary and read-only recovery; 0143 unchanged
S22 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b6a_expense_cash_foundation.md | 10B6a paid expense and cash movement foundation; sole head 0144; 293 full-suite failures by count
S23 | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10f3_checkout.md | Business 10F3 Service checkout, grants, methods, corrections, refunds and protected receipts
S24 | C:\NIHILOBA\nihiloba-website\docs\restaurants_rm_v11_10f3_checkout.md | Website 10F3 Service checkout and private guest payment summary
S25 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b6b_daily_closing.md | 10B6b confirmed-zone daily close, 0145 sole head, focused/PostgreSQL passes and unresolved full-suite comparison
S26 | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10f4_daily_operations.md | Business 10F4 owner daily operations and real-Backend browser acceptance
S27 | C:\NIHILOBA\nihiloba-website\docs\restaurants_rm_v11_10f4_daily_operations.md | Personal 10F4 owner daily operations and real-Backend browser acceptance
S28 | Founder request in this chat (2026-10-11) | Add QR auto-accept, fixed-table QR and simple reservations; reservations require a SHIDA account
S29 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_guest_qr_auto_accept.md | Optional Free guest QR auto-accept across Backend and both frontends; sole head 0146
S30 | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_fixed_tables.md | Paid Business fixed-table QR and table-delivery implementation; sole head 0147
S31 | C:\NIHILOBA\Backend\docs\restaurants_simple_reservations.md | Free account-based seller-confirmed Restaurant reservations; sole head 0148
S32 | C:/NIHILOBA/nihiloba-website/docs/restaurants-settings-2026-10-15.md | Local Settings: 25 browser checks, 132 unit executions, 525 Backend passes / 2 expected skips. Live acceptance open.
S33 | C:/NIHILOBA/nihiloba-website/docs/restaurants-receiving-2026-10-15.md | 52 production-browser cases; 116 Website unit and 253 Backend executions pass. Release Partial; live acceptance and reusable schedules open.