## Overview
SHIDA Restaurants & Malewa — release validation
Checkpoint: 15 October 2026 ¦ local Alembic head 0159 ¦ Personal Reservations and Menu page batches
Personal Reservations and Menu implemented locally. Release Partial; full gates and live acceptance open.
Gate | Total | Passed | Remaining
Manual journeys | 62 | 0 | 62
Historical automation | 31 | 18 | 13
Launch steps | 15 | 0 | 15
Restaurant pilot automated gate | Fail
Blocking issues open | 2
Release status | Needs validation
How to update
1. Run a check. Set Pass, Fail, Blocked or Not applicable; add owner, date and evidence link or issue.
2. Resolve blocking issues; use Sources and runs to record environment and exact commit.
3. A green count means evidence is complete, not automatic approval to release.
Current highest-priority work
Backend broad gate previously recorded: 2,763 passed / 58 failed / 21 expected skips. Reservations and Menu focused checks recorded below; Website full suite and lint remain red. Staging, real WhatsApp phone, devices and language review open. Release Partial.
Founder scope: historical platform-wide suite remains red, outside this Restaurant pilot gate. No deployment or intake.

## Manual journeys
Manual journeys
Use real phones, real staff and controlled stock/money. Enter owner, date and evidence when a check is run.
ID | Area | Actor | Channel | Action / scenario | Expected result | Priority | Status | Owner | Test date | Evidence / issue
M01 | Setup | Owner | Website | Open a Free Restaurant/Malewa profile, publish menu and general QR. | Public page and menu show the right establishment; no table setup required. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M02 | Setup | Owner | Website | Set opening hours and close new order intake. | Closed intake refuses new orders; outstanding orders stay manageable. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M03 | Setup | Owner | Website | Compare Free, Personal Pro and Business Pro destinations. | Controls follow the current tier and exact ownership. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M04 | Setup | Owner | Dashboard | Grant, change and revoke Service/Kitchen/Bar/Stock/money assignments. | Workers see only assigned establishment and allowed actions; revocation takes effect. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M05 | Setup | Owner | Dashboard | Downgrade paid access with unfinished orders and money obligations. | New paid work closes; permitted owner recovery remains available. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M06 | Public menu | Customer | Phone web | Open public menu in FR/EN/LN/SW and view food prices. | Names, prices, CDF/USD, availability and wording are understandable. | Must | Not run | Pilot lead + Customer |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M07 | Public menu | Customer | WhatsApp | Use Restaurant profile/menu path in four languages. | No retired reservation shortcut or prohibited alcoholic-drink promotion appears. | Must | Not run | Pilot lead + Customer |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M08 | Guest QR | Guest | Phone web | Scan general QR without a SHIDA account and start a visit. | Private visit is created; QR itself exposes no private order. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M09 | Guest QR | Guest | Phone web | Quote basket, submit first round, retain visit reference. | One immutable round appears with correct reference, status and currency. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M10 | Guest QR | Guest | Phone web | Add a drink as a second round in the same visit. | New order is created; summary shows both rounds and combined eligible totals. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M11 | Guest QR | Two guests | Phone web | Order separately from the same general QR or same fixed table. | Visits, bills and private pickup proof remain separate. | Must | Not run | Pilot lead + Two guests |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M12 | Guest QR | Guest | Phone web | Attempt to open another visit with order number or public QR. | Private details and pickup proof remain inaccessible. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M13 | Guest QR | Guest | Phone web | Lose the private visit cookie or switch device. | No unauthorized recovery; supporter can explain the limit. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M14 | Guest QR | Guest | Phone web | Use slow connection and retry an uncertain submission. | Exact retry avoids duplicate order and explains final state. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M15 | Guest QR | Seller | Owner screen | Accept then reject separate pending guest rounds. | Statuses and totals reflect each actual decision; rejected round is not a completed sale. | Must | Not run | Pilot lead + Seller |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M16 | Guest QR | Owner | Owner screen | Turn auto-accept off/on and submit valid guest QR order. | Off stays pending; on uses canonical acceptance and stock reservation. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M17 | Guest QR | Owner | Owner screen | Submit with auto-accept on but insufficient stock. | Order remains pending for seller decision; no false acceptance. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M18 | Guest QR | Guest | Phone web | Cancel eligible round and inspect summary. | Cancelled status and totals remain truthful. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M19 | Pickup | Guest | Phone web | Request ready-only private pickup code, then collect. | Code appears only when ready; order number alone never proves pickup. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M20 | Pickup | Worker | Dashboard | Attempt pickup without private proof or correct authority. | Handover is refused; legitimate proof works once. | Must | Not run | Pilot lead + Worker |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M21 | Fixed tables | Owner/Admin | Dashboard | Create and label a fixed table; print/share table QR. | Exact label and QR work; general QR still works. | Must | Not run | Pilot lead + Owner/Admin |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M22 | Fixed tables | Owner/Admin | Dashboard | Rotate table QR then retire table. | Old QR cannot start a new table visit; existing rounds retain label. | Must | Not run | Pilot lead + Owner/Admin |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M23 | Fixed tables | Guest | Phone web | Order twice from table QR and receive table delivery. | Both immutable rounds stay in private visit; handover is attributed. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M24 | Fixed tables | Owner | Dashboard | Check Free/Personal and staff cannot manage paid Business tables. | Controls and protected actions are denied. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M25 | Service | Waiter | Dashboard | Take an assisted order and attest physical handover. | Accepted order enters preparation; handover happens only when ready. | Must | Not run | Pilot lead + Waiter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M26 | Service | Waiter | Dashboard | Ask guest to approve association with private visit. | Only the consenting guest visit is linked; no automatic shared bill. | Must | Not run | Pilot lead + Waiter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M27 | Service | Waiter | Dashboard | Use same Service screen to record declared cash/mobile-money payment. | Correct method and CDF/USD allocation are recorded; no provider verification claim. | Must | Not run | Pilot lead + Waiter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M28 | Service | Waiter | Dashboard | Retry uncertain payment with identical request. | No duplicate money record; changed request is rejected. | Must | Not run | Pilot lead + Waiter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M29 | Preparation | Kitchen/Bar | Dashboard | Process food and non-alcoholic drink station lines separately. | Correct station sees assigned lines; whole order ready only when all required lines ready. | Must | Not run | Pilot lead + Kitchen/Bar |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M30 | Preparation | Owner | Dashboard | Recover blocked preparation after worker access loss. | Recovery is attributed; no unauthorized station access. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M31 | Stock | Stock worker | Dashboard | Receive countable stock and record ingredient use in units/kg. | Quantities and audit match actual entries; no automatic recipe deduction claim. | Must | Not run | Pilot lead + Stock worker |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M32 | Stock | Stock worker | Dashboard | Count, waste and correct stock; attempt another establishment. | Each permission is separate and exact-establishment access enforced. | Must | Not run | Pilot lead + Stock worker |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M33 | Stock | Two actors | Dashboard | Sell last item while stock worker adjusts quantity. | No oversell or double consumption. | Must | Not run | Pilot lead + Two actors |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M34 | Money | Owner/Waiter | Dashboard | Record partial CDF and USD payments without conversion. | Two currency balances are separate and correct. | Must | Not run | Pilot lead + Owner/Waiter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M35 | Money | Owner/Waiter | Dashboard | Correct a mistaken entry and record an actual refund. | Correction and actual money-out remain distinct; receipt is truthful. | Must | Not run | Pilot lead + Owner/Waiter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M36 | Money | Guest | Phone web | View approved private payment summary. | Amounts reflect recorded evidence only; no paid/verified claim without basis. | Must | Not run | Pilot lead + Guest |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M37 | Daily work | Owner | Owner screen | Attest opening cash during local day for CDF and USD. | Opening amounts save once; zero and missing remain distinct. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M38 | Daily work | Owner | Owner screen | Enter expense, cash in/out and count cash. | Expense and drawer movement remain distinct with correct totals. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M39 | Daily work | Owner | Owner screen | Preview current day and check outstanding orders/refunds/stock exceptions. | Report shows separate cash, mobile money and outstanding items. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M40 | Daily work | Owner | Owner screen | Close local day after midnight and inspect signed report. | Close is immutable, discrepancy visible and no order/bill is silently settled. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M41 | Daily work | Owner | Owner screen | Post a permitted later correction after close. | Supplement appears without rewriting original report. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M42 | Daily work | Owner | Owner screen | Miss opening attestation, then attempt retrospective entry. | System refuses retrospective override; supporter can explain limitation. | Should | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M43 | Reservations | Customer | Website | Sign in with Personal account; request date/time/party. | Private request is created, with no order, deposit or table assignment. | Must | Not run | Pilot lead + Customer |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M44 | Reservations | Customer | Website | View and cancel own pending/accepted request. | Only exact customer can see or cancel; state refreshes. | Must | Not run | Pilot lead + Customer |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M45 | Reservations | Seller | Owner screen | Accept, reject, cancel, mark arrival and complete separate bookings. | Each step uses current revision; overlap and status are clear. | Must | Not run | Pilot lead + Seller |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M46 | Reservations | Seller | Owner screen | Close reservation intake or test takeaway-only establishment. | No new requests; accepted commitments remain manageable. | Must | Not run | Pilot lead + Seller |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M47 | Reservations | Customer/Seller | WhatsApp | Make and respond to reservation in FR/EN/LN/SW. | Correct profile path, privacy and status messages in each language. | Must | Not run | Pilot lead + Customer/Seller |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M48 | Reservations | Customer | Website | Allow pending request to reach its deadline. | It expires accurately and cannot be accepted late. | Must | Not run | Pilot lead + Customer |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M49 | Notifications | Seller/Customer | WhatsApp | Simulate provider failure and later recovery. | Domain decision remains correct; sent/accepted is not described as delivered/read. | Must | Not run | Pilot lead + Seller/Customer |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M50 | Privacy | Other account | Phone/Dashboard | Try cross-customer and cross-organization reads/actions. | All private visits, money, booking and staff data are denied. | Must | Not run | Pilot lead + Other account |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M51 | Privacy | Owner | Admin workflow | Erase account or reach retention deadline with held records. | Direct identity removed where required; preserved business evidence remains bounded. | Must | Not run | Pilot lead + Owner |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M52 | Release UX | Customer/Worker | Real phone | Run full counter and table journey on low bandwidth and narrow screen. | No blocking layout, stale state or duplicate action. | Must | Not run | Pilot lead + Customer/Worker |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M53 | Release UX | Supporter | Review | Review all four-language customer and worker wording with real speakers. | Confusing text and WhatsApp flow improvements logged. | Must | Not run | Pilot lead + Supporter |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M54 | Pilot day | Restaurant team | On site | Run one opening-to-close working day with guest, waiter, kitchen, bar, stock and owner. | Orders, handovers, money and closing reconcile against observed reality. | Must | Not run | Pilot lead + Restaurant team |  | Physical pilot/device/provider acceptance remains to be run; record observed evidence and date.
M55 | Reservations | Restaurant seller | Phone / tablet / desktop | Review month, selected day and pending requests; open a booking and take a current-revision action. | Only the exact establishment is shown. Pending requests outside the viewed month stay clear; changes refresh the calendar. | Must | Not run | Pilot lead + Seller |  | Calendar batch 1 is locally tested only; physical device and staging acceptance remain open. See Backend/docs/shared_calendar_batch1.md.
M56 | Reservations | Customer | Real phone | Choose a local reservation date and time, including month and clock-boundary cases. | Date and time are clear in FR/EN/LN/SW; invalid local times are refused; request remains subject to seller confirmation. | Must | Not run | Pilot lead + Customer |  | Local responsive and Backend checks passed; real-phone and native-language review remain open. See Backend/docs/shared_calendar_batch1.md.
M56 | Solo Malewa | Personal owner + customer | Real phone / Website / WhatsApp | Accept an all-ready-to-serve pickup, show the customer code, then confirm actual handover. | Ready follows availability confirmation. Handover and payment remain separate; FR/EN/LN/SW wording is accepted by people. | Must | Not run | Pilot lead + language reviewers |  | Authenticated staging, real WhatsApp phone and physical-device acceptance remain open.
M57 | Mixed order | Personal owner + customer | Real phone / Website / WhatsApp | Accept ready-to-serve and made-to-order items together; finish preparation, cancellation and pickup/delivery checks. | The order is ready only after required work finishes. Receipt, CDF/USD and money ledger remain canonical. | Must | Not run | Pilot lead + language reviewers |  | Observed workday, physical devices and human language review remain open.
M58 | Solo Stock | Personal Restaurant owner | Real phone / Website / WhatsApp | Count prepared portions, packaged units and ingredients; receive, waste and recount; verify menu shortage, sale, cancellation and retry. | Physical quantities and movement history match observation; no expense or payment is inferred. FR/EN/LN/SW wording accepted by people. | Must | Not run | Pilot owner + language reviewers |  | Local seeded checks only. Authenticated staging, real WhatsApp phone, physical devices and human language acceptance open.
M59 | Solo Finances | Personal Restaurant or Malewa owner | Authenticated staging / real device | Record CDF and USD cash/mobile receipts, a cash-paid expense, opening and closing counts, an unpaid bill and a refund obligation; review an exact-reference bill and close after local midnight. | Observed cash and recorded methods reconcile by currency; missing opening stays missing, current bill obligations remain separate from daily money, and no provider verification or profit is claimed. | Must | Not run | Pilot owner + language reviewers |  | Local focused checks passed. Authenticated staging, real phone/tablet, physical cash/count and FR/EN/LN/SW human review remain open.
M60 | Solo Reservations | Personal Restaurant or eligible seated-service owner + guest | Authenticated staging / real WhatsApp phone / physical device | Request a visit by Website and WhatsApp, accept and decline separate requests, refresh, view the local-day agenda and calendar, cancel, record arrival and complete a visit. | References, times and party sizes remain accurate; guest notices and status retrieval work without duplicate responses. Accepting creates no order, bill, payment, table assignment or guaranteed capacity. | Must | Not run | Pilot owner + language reviewers |  | Local seeded browser 16/16 pass; isolated real Backend journey 1/1 pass; Backend focus 45 passed / 2 skipped. Seller record does not expose guest name or distinguish Website from WhatsApp source. Authenticated staging, real phone/provider, physical devices and human FR/EN/LN/SW review open.
M61 | Solo Menu | Personal Restaurant or Malewa owner + guest | Authenticated staging / real WhatsApp phone / physical device | Create an unavailable item, explicitly choose Ready to serve, Kitchen or Bar, set price and availability, add stock/dated-offering controls where supported, then select through Selling, public menu and WhatsApp. | Current availability and exact currency govern new selection; stale selection is rejected. Accepted orders retain their captured item details and route. No inferred ingredient consumption, expense, FX conversion or mixed-currency order. | Must | Not run | Pilot owner + language reviewers |  | Local production-build browser 16/16 pass; Website focused 82/82 and Backend focused 28/28 pass. Authenticated staging with real stock and dated offerings, real WhatsApp provider, physical devices and human FR/EN/LN/SW review open.

## Automated checks
Automated checks
A01-A31 retain historical results. P01 onward records the dedicated Restaurant pilot automated gate; live acceptance is separate.
ID | Repository | Check | Expected gate | Prior local evidence | Priority | Status | Owner | Run date | Evidence / issue
A01 | Backend | Verify sole current Alembic head 0150 and lineage through Restaurant 0148 and Services 0150. | Exactly one head; no branch drift. | 0148 reported sole head after reservations. | Must | Pass | Backend / database engineer | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_full_suite.json: sole Alembic head 0150; revision d6c5fbbe6aa541d651e266f77fc4b99e3b81efb2
A02 | Backend | Apply populated 0147→0148→0149 migration in designated staging PostgreSQL. | Upgrade succeeds; preserved orders/money/table data. | Reservation handoff did not run live PostgreSQL. | Must | Blocked | Database / release engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\postgres_populated_verification.txt (disposable only); staging not accessed
A03 | Backend | Rehearse populated 0147→0148→0149 and populated 0149→0150 locally. | All constraints/indexes and maintenance paths work. | Fresh-schema focused and DDL compilation passed locally. | Must | Pass | Database engineer | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\postgres_populated_verification.txt (earlier 0147→0149); backend_closure_populated_0149_to_0150.json; backend_closure_pg_migration.txt (disposable only)
A04 | Backend | Historical platform-wide Backend suite (outside Restaurant pilot scope by founder decision, 12 October 2026). | Classify every failure against tracked baseline; zero unexplained new failures. | 0146 broad pre-final; 0147 interrupted; 0148 stopped at inherited Employment fixture. | Must | Fail | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_full_suite.json: 8076 pass/168 fail/1005 skip; 6 prior IDs resolved; 1 new vs prior closure; revision d6c5fbbe6aa541d651e266f77fc4b99e3b81efb2; diff SHA256 a50adbd6bde7ae24384788dedf4c69890bd8ab1a4a4c103291b9dcfbc0ff765c
A05 | Backend | Run focused Restaurant regression suite on exact release commit | Guest, tables, reservations, Service, prep, stock, money, closing pass. | Focused batch selections passed independently. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_six_after.xml: 6/6; restaurant_three_files.xml: 126 pass/5 skip; restaurant_related.xml: 235 pass/2 skip
A06 | Backend | Run PostgreSQL last-stock and replay races | No oversell, double reserve, consume or payment. | Earlier batch PostgreSQL races passed; 0148 live server unavailable. | Must | Pass | Backend / database QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: stock_retention; stock_worker_preparation_final; nine named groups 168 pass/0 fail/2 skip; head 0150
A07 | Backend | Test QR auto-accept on/off, invalid quote and shortage | Canonical accepted or pending result with provenance. | 125 focused and 10 PostgreSQL passed for 0146 batch. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: auto_accept; nine named groups 168 pass/0 fail/2 skip; head 0150
A08 | Backend | Test table QR rotation/retirement, label snapshot and guest isolation | Stale QR cannot start new visit; history stays accurate. | 65+7 focused and 7+2 PostgreSQL passed for 0147 batch. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: guest; nine named groups 168 pass/0 fail/2 skip; head 0150
A09 | Backend | Test reservation concurrency, deadline and authority | One current decision; stale revision denied; exact ownership. | 108 focused, 6 policy/schema and 89 migration tests passed; no live PostgreSQL. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: reservations_durable; nine named groups 168 pass/0 fail/2 skip; head 0150
A10 | Backend | Test seller and worker grant revocation during action/replay | Current authority rechecked; old cursor/retry cannot escalate. | Earlier B2–B4 focused checks passed. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: service_durable; stock_worker_preparation_final; nine named groups 168 pass/0 fail/2 skip; head 0150
A11 | Backend | Test private visit cookie, pickup proof and cross-visit access | QR/order number never grants private authority. | 09B1/09B2 focused tests passed locally. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: guest; order_projection; nine named groups 168 pass/0 fail/2 skip; head 0150
A12 | Backend | Test Kitchen/Bar line routing and once-only stock consumption | Aggregate readiness and stock remain canonical. | 10B3 focused/PostgreSQL passed. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: stock_worker_preparation_final; nine named groups 168 pass/0 fail/2 skip; head 0150
A13 | Backend | Test CDF/USD allocation, corrections, refunds and receipts | Separate currencies; no FX or provider verification claims. | 10B5/10F3 focused and real-Backend checks passed. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: money_replay_durable; daily_financial_durable; nine named groups 168 pass/0 fail/2 skip; head 0150
A14 | Backend | Test daily closing at local-day edge with concurrent writes | Correct close boundary, immutable report and later supplement. | 10B6b 54 SQLite and 10 PostgreSQL passed. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: daily_financial_durable; nine named groups 168 pass/0 fail/2 skip; head 0150
A15 | Backend | Run retention, erasure, preservation and maintenance checks | Expired data handled; held evidence preserved and minimized. | Batch handoffs report focused coverage; operation not accepted live. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_pg_groups.json: stock_retention; maintenance_durable; nine named groups 168 pass/0 fail/2 skip; head 0150
A16 | Backend | Test closed intake, downgrade and outstanding recovery | New intake refused; existing obligations resolvable. | Focused checks exist across batches. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_six_after.xml; restaurant_related.xml: admission-loss recovery and current proof paths passed
A17 | Backend | Compile Python and duplicate translation keys | No syntax or duplicate-key errors. | Passed in recent handoffs. | Must | Pass | Backend QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_static.txt: compilation and duplicate translation-key check passed
A18 | Backend | Inspect log/privacy assertions in full suite | No secrets, private visit tokens or pickup proofs leak. | Earlier 12 privacy logging checks passed; final suite pending. | Must | Partial | Backend security QA | 2026-10-12 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\backend_closure_restaurant_focused.xml (Restaurant privacy passed); backend_closure_final_suite.json (inherited Employment listing privacy assertion remains blocked at navigation)
A19 | Website | Run production build and typecheck | Both succeed on exact release commit. | Passed for 0146–0148 feature batches. | Must | Pass | Website engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\website_build_current.txt; website_typecheck_final.txt: final-source build/typecheck passed
A20 | Website | Run full unit/browser suites and baseline comparison | Zero unclassified new failures; record inherited failures. | Earlier 8 Website unit failures and 17 browser failures documented; final comparison pending. | Must | Fail | Website QA | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\website_units_final.txt: 376 pass/4 inherited fail; website_browser_final_verified.txt: 74 pass/32 skip; website_31_identity_disposition.json: 31 fixture-related
A21 | Website | Run lint and classify all findings | No new findings; inherited 9 errors/2 warnings tracked. | Changed-file lint passed; repo lint inherited findings. | Must | Fail | Website engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\website_lint_current.txt: inherited 9 errors/2 warnings
A22 | Website | Run real-Backend guest, table, reservation and money browser flows against current head 0149. | All customer flows pass with 0148 Backend. | Separate feature browser flows passed; not one final-stack run. | Must | Partial | Website / Business QA | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\website_reservation_real_backend_final.txt: 1 cross-surface reservation; integrated_website_guest_full_final.txt: 20 pass; integrated_website_service.txt: 3 pass; Business money browser: 1 pass. Separate SQLite fixtures, not migrated-head browser acceptance
A23 | Business | Run production build and typecheck | Both succeed on exact release commit. | Passed for 0146–0148 feature batches. | Must | Pass | Business engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\business_build_current.txt; business_typecheck_latest.txt: current-source build/typecheck passed
A24 | Business | Run full units/browser and baseline comparison | Zero unclassified new failures; inherited 20 unit failures tracked. | Earlier full suite retained 20 inherited failures. | Must | Pass | Business QA | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\business_units_final.txt: 496 passed; business_browser_current.txt: 34 pass/8 documented real-Backend skips/0 fail
A25 | Business | Run lint and classify findings | No new findings; inherited 2 errors/1 warning tracked. | Changed-file lint passed; repo lint inherited findings. | Must | Fail | Business engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\business_lint_latest.txt: inherited 2 errors/1 warning; no new lint finding
A26 | Business | Run real-Backend owner/staff journey against current head 0149. | Tables, reservations, Service, stations, stock and close work together. | Separate browser flows passed, not final integrated run. | Must | Partial | Business / Backend QA | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\integrated_business_operations.txt: Service/money/daily 3 pass, preparation fixture reset needed; integrated_business_preparation_corrected.txt: 1 pass; integrated_business_stock.txt: 1 pass. Separate journeys; retired combined fixture and observed workday open
A27 | Integrated | Load test shared guest proxy and QR submission rate limits | Capacity and abuse limits meet intended pilot traffic. | 09B2 handoff flags shared proxy capacity. | Must | Partial | Backend / Website engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\https_guest_proxy_probe.txt: 12 separate browsers admitted; 11th visit from one browser 429 with Retry-After; 300 aggregate cap not load accepted
A28 | Integrated | Verify production-like TLS, Origin, cookie and cache settings | Private visits and protected APIs work without cross-origin leakage. | Live configuration acceptance pending. | Must | Partial | Infrastructure / release engineer | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\https_guest_proxy_probe.txt: local TLS, Origin, private cookie/cache, visit isolation passed; deployed direct-port isolation untested
A29 | Integrated | Exercise WhatsApp message retry/provider failure in four languages | Correct recovery; no false delivery/read claim. | Backend photo checks and Personal web upload/recovery confirmed locally in FR/EN/LN/SW. Real-phone and Meta acceptance pending. | Must | Blocked | Meta operations + language reviewers | 2026-10-12 | Backend restaurants_photo_contract.md; Website docs/restaurants-mobile-photos.md. Native language and live provider acceptance still required.
A30 | Integrated | Run maintenance jobs against current schema | Expiry, retention and notification recovery execute safely. | Existing runner reused; live operation pending. | Must | Partial | Database / operations engineer | 2026-10-12 | Existing maintenance now includes bounded photo orphan/replacement cleanup and preservation holds. See restaurants_photo_contract.md; live provider cleanup remains open.
A31 | Integrated | Check final docs, rollout order and diff cleanliness | 0151 then Backend/maintenance then web photo editor; no intake enablement. | Handoffs describe rollout; no deployment. | Must | Blocked | Release lead + support lead | 2026-10-11 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\git diff --check passed; tracker review structurally verified; guide left staged by user instruction pending every-page render; live release acceptance open
P01 | All three | Restaurant pilot automated gate | Every required scoped check passes; no unexplained skips. | Separate from historical platform-wide failures. | Must | Fail | Pilot engineering | 2026-10-14 | C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: MGT01 implementation and scoped corrections pass. Consolidated final-tree gate, complete browser sets and staging acceptance remain required. 2026-10-14 seller workspace gate: 2763 passed / 58 failed / 21 skipped (0 unexpected skips); results and failed nodes: Website .s3a-local/restaurant-workspace-gate-2026-10-14/summary.json.
P02 | Backend | Restaurant and shared SQLite tests | Required scoped check | Current combined source; exact selection in inventory. | Must | Fail | Pilot engineering | 2026-10-14 | 2476 passed / 0 failed / 17 reviewed skips; includes 28 exact adjacent cases. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Diagnostic: 2691 pass / 113 fail / 21 skip. All observed failures resolved by focused reruns (89 + 1 + 42 + 16 passing executions); zero unexpected skips. No new uninterrupted frozen-tree full run. 2026-10-14 Backend SQLite gate: 2763 passed / 58 failed / 21 skipped (0 unexpected skips). Failures: 49 stale 0152-head assertions versus concurrent 0156, 6 guarded service-bill downgrade cases, 1 guarded-message mismatch, 2 Service index / Wenze migration checks. Exact nodes: Website .s3a-local/restaurant-workspace-gate-2026-10-14/summary.json.
P03 | Backend | PostgreSQL races, shared controls and migration runtime checks | Required scoped check | Current combined source; exact selection in inventory. | Must | Pass | Pilot engineering | 2026-10-13 | 462 passed / 0 failed or unexpected skips / 4 Organization-only skips; 14 named disposable groups. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: PostgreSQL gate: 460 pass / 2 stale-head failures / 4 documented skips initially; affected assisted group rerun 15 pass, added photo races 4 pass. Distinct corrected coverage 466 pass / 4 expected skips; zero unexpected skips.
P04 | Backend | Fresh migration upgrade, sole head and PostgreSQL offline DDL | Required scoped check | Current combined source; exact selection in inventory. | Must | Pass | Pilot engineering | 2026-10-13 | Fresh upgrade to sole 0150; PostgreSQL 0149:0150 offline compilation and Restaurant round trips passed. fsync/full_page_writes/synchronous_commit=on. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Fresh disposable PostgreSQL upgrade to sole head 0152 and offline 0149:head DDL passed. Existing migration targets preserved; no migration introduced by MGT01.
P05 | Website | Restaurant and necessary shared frontend unit tests | Required scoped check | Current combined source; exact selection in inventory. | Must | Pass | Pilot engineering | 2026-10-14 | 311 passed / 0 failed / 0 skipped. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Website scoped Restaurant/shared session/security unit tests: 353 passed, 34 files. 2026-10-14 Website scoped Restaurant/shared unit gate: 320 passed, 0 failed, 0 skipped. Website .s3a-local/restaurant-workspace-frontend-final2-2026-10-14/.
P06 | Business | Restaurant and necessary shared frontend unit tests | Required scoped check | Current combined source; exact selection in inventory. | Must | Pass | Pilot engineering | 2026-10-14 | 350 passed / 0 failed / 0 skipped. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Business Restaurant/capability/auth tests: 297 passed, 25 files. 2026-10-14 Business scoped Restaurant/shared unit gate: 350 passed, 0 failed, 0 skipped. Website .s3a-local/restaurant-workspace-frontend-final2-2026-10-14/.
P07 | Website | Complete Restaurant browser set with shared sign-in | Required scoped check | Current combined source; exact selection in inventory. | Must | Partial | Pilot engineering | 2026-10-14 | 104 passed; zero skipped, unexpected or flaky required. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Final seller scope: 60 browser tests passed on production preview, all four locales. Complete public/guest fixture suite and staging shared sign-in are not claimed. 2026-10-13 workflow follow-up: Website production preview 36 management/seller browser checks and 4 new seeded workflow checks passed; complete pilot/public and staging checks remain outstanding. 2026-10-13 workflow verification: Website production build passed; 12/12 seeded workflow browser checks passed at 360/820/1440, including canonical counter quote, handover, bill, CDF receipt and finance totals. Complete public/guest and staged sign-in remain open. 2026-10-14 seller scope: Website 29 mocked browser checks passed at 360/820/1440 across FR/EN/LN/SW, including empty/closed intake, inline routing and keyboard; 3 real Backend service/money checks passed. Full browser inventory and staging remain open. 2026-10-14 Selling: 12/12 local FR/EN/LN/SW browser checks at 360/820/1440; counter handover/payment passed. Shared-sign-in and staging remain open. 2026-10-14 Orders page follow-up: Website production build, typecheck, changed-file lint and 308 scoped Restaurant tests pass (135 focused subset). 44 production-server browser checks pass, including FR/EN/LN/SW at 360/820/1440 px, closed intake, history and existing Today/Selling workflow checks. Seeded UI evidence only; real device and live authenticated acceptance remain open. Website docs/restaurants-orders-2026-10-14.md. Backend scoped gate remains separately red (2763 passed / 58 failed / 21 skipped).
P08 | Business | Complete Restaurant browser set with shared sign-in | Required scoped check | Current combined source; exact selection in inventory. | Must | Partial | Pilot engineering | 2026-10-14 | 15 passed; zero skipped, unexpected or flaky required. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: 3 new Business responsive/language checks passed at 360/820/1440. Legacy complete Business browser fixtures still need Orders-first navigation updates. 2026-10-13 workflow follow-up: Business local build, typecheck, 40 focused unit tests and 3 responsive management browser checks passed; full Business Restaurant gate remains outstanding. 2026-10-13 workflow verification: Business production build and 3/3 responsive management browser checks passed; 40 focused unit tests passed. Complete Business Restaurant browser scope remains open. 2026-10-14 Business: 12 responsive management browser checks passed across FR/EN/LN/SW at 360/820/1440, plus one real Backend Organization owner and assigned worker service journey. Full browser inventory and staging remain open. 2026-10-14 Selling: 12/12 local FR/EN/LN/SW Business browser checks at 360/820/1440; mounted POS/Service 7/7. Live staff and staging remain open.
P09 | Website + Business | typecheck | Required scoped check | Current combined source; exact selection in inventory. | Must | Pass | Pilot engineering | 2026-10-14 | All recorded commands exit 0; see exact commands/logs in typecheck-final4. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Both production builds passed including TypeScript. Generated Business next-env path churn restored. 2026-10-14 Website and Business production builds passed TypeScript.
P10 | Website + Business | lint | Required scoped check | Current combined source; exact selection in inventory. | Must | Partial | Pilot engineering | 2026-10-14 | All recorded commands exit 0; see exact commands/logs in lint-final5. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: All modified frontend implementation and new management tests lint clean. Whole-repository lint was not rerun. 2026-10-14 Changed Restaurant source and browser tests linted without errors; whole repositories not rerun.
P11 | All three | static | Required scoped check | Current combined source; exact selection in inventory. | Must | Partial | Pilot engineering | 2026-10-13 | All recorded commands exit 0; see exact commands/logs in static-final3. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Changed Python syntax and all repository diff checks passed; exact skip manifests checked. Full platform static suite not rerun.
P12 | Website + Business | Production builds | Required scoped check | Current combined source; exact selection in inventory. | Must | Pass | Pilot engineering | 2026-10-14 | Both Next production builds exited 0. App, dependency and build configuration sources remain unchanged throughout fixture fixes. ¦ C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json 2026-10-13 MGT01: Website and Business production webpack builds passed locally. 2026-10-14 Website and Business Next production builds passed locally.
MGT01 | Website / Backend / Business | Restaurant seller management and temporary pre-purchase access | Responsive authenticated workspace; exact ownership, grants, intake and existing obligations preserved | 2026-10-13 local working trees; no deploy, commit or push | Must | Partial | Restaurant engineering | 2026-10-14 | Website docs/restaurants-management-2026-10-13.md: responsive screenshots and scoped checks. Staging/physical-device acceptance and complete pilot rerun remain required. 2026-10-13 MGT01: Implemented and scoped validation complete; 60 Personal + 3 Business browser checks, 353 + 297 unit tests, 185 Backend policy checks, 90 focused PostgreSQL checks. Pilot diagnostic failures resolved by focused reruns. See Website docs/restaurants-management-2026-10-13.md for all evidence and remaining final-tree/browser/staging gates. 2026-10-13 seller workflow follow-up: Website and Business local task navigation/copy, Orders, statistics, counter basket and reservation fixes; Website production browser 36 existing + 4 new seeded cases passed at 360/820/1440, 138 scoped units; Business 3 responsive browser checks and 40 focused units passed. Counter payment method and establishment-wide finance aggregation require canonical Backend contracts. Live capability response, human FR/LN/SW review, physical devices and staging remain open. No deploy/commit/push. Website/docs/restaurants-management-2026-10-13.md 2026-10-13 workflow verification: Local Website, Backend and Business seller workflow correction. Counter handover now links one canonical closed bill; existing payment methods, receipt, replay, stock and money ledger apply. Daily report now separates linked order value, recorded collections, outstanding, expenses and cash variance by CDF/USD. Disposable PostgreSQL gate: 466 passed, four documented skips before final contract additions; focused post-change SQLite tests pass; six targeted PostgreSQL cases pass. Authenticated deployed capability is unverified (HTTP 401 without session). Broad SQLite diagnostic: 2,809 pass, 21 documented skips, one stale test fixed and exact-rerun passed. Final-tree full rerun, human FR/LN/SW review, physical devices and staging remain open. No deploy, commit or push. 2026-10-14 seller workspace: Today, grouped selling, inline Kitchen/Bar routing and responsive navigation in Website and Business. Frontend scoped units 320 + 350 passed; 29 Website and 12 Business mocked browser checks passed, plus real Backend Personal and Organization service/money journeys. Builds, typechecks and changed-file lint passed. Scoped Backend gate 2763 passed / 58 failed / 21 skipped (0 unexpected skips); release remains Partial. Website docs/restaurants-seller-workspace-2026-10-14.md. No deploy, production intake, commit or push.
CAL01 | Backend / Website / Business | Shared calendar batch 1 | Restaurant exact-scope seller calendar and customer date picker pass focused checks; Services and Apartments remain separate pending adapters. | 14 Oct local implementation; no deployment, commit or push. | Must | Partial | Restaurant / platform engineering | 2026-10-14 | Backend/docs/shared_calendar_batch1.md: Restaurant 45 pass/2 expected skips; Services and Apartment privacy 54 pass; both web builds/typechecks/focused lint and calendar tests pass; responsive 6 Website + 3 Business; one real-Backend HTTPS journey pass. Services browser fixtures fail existing ServicesTemplatePicker undefined rows; Services/Apartment calendars not mounted. No complete final-tree gate or live acceptance. Sole Alembic head 0156.
CUX01 | Website | Customer marketplace and menu redesign | Published listings, truthful menu and fulfillment, existing guest quote and recovery; local browser evidence; physical and live acceptance separate. | 2026-10-13 local Website working tree; no deployment, commit or push. | Must | Partial | Website Restaurant engineering | 2026-10-13 | Website docs/restaurants-customer-redesign.md; 80 focused unit passes, typecheck/build/changed-file lint pass. Real local Backend: 20/21 combined guest+redesign browser cases first run; stale seller navigation test corrected and passed alone. Discovery/detail fixture browser: 15/16 then desktop sparse-card fix passed alone. Phone/tablet/desktop screenshots in Website docs/evidence/restaurants-customer-redesign/. Physical devices, native-language and live acceptance remain open.
SOLO01 | Backend + Website | Solo ready-to-serve, mixed Orders and WhatsApp | Canonical acceptance, preparation and handover; four languages and both WhatsApp reply modes; responsive Website checks. | Prior order and worker flows remain authoritative. | Must | Partial | Restaurant engineering | 2026-10-14 | Affected Backend suite: 371 passed; assisted ready-to-serve: 2 passed; migration: 2 passed; automatic acceptance, assisted orders and tables: 71 passed. Local migration to 0158, Website build/typecheck/lint, 103 focused unit tests and 50 seeded browser checks passed. Live phone, staging, physical device, human language acceptance and broader Backend gate remain open.
STOCK01 | Backend + Website + WhatsApp | Personal Stock daily workspace | Seller-declared stock kind and explicit legacy classification; revisioned receive/waste/count, movement balances, menu binding and four-language responsive page. | Backend head 0159; uncommitted local working trees; Business unchanged. | Must | Partial | Restaurant engineering | 2026-10-15 | Stock/API/WhatsApp: 70 passed initially, 34 passed after classification and HTTP tests; Organization stock worker: 33 passed; preparation/assisted/WhatsApp journeys: 348 passed; final WhatsApp wording and new migration checks: 22 passed; targeted migration/head checks: 4 passed. Separate order/migration run: 79 passed / 2 obsolete fixed-head assertions failed; assertions updated and targeted checks rerun. Website: build/typecheck and changed-file lint passed; 91 focused unit tests passed; 14/14 seeded production-server Chrome checks passed, including FR/EN/LN/SW at 360/820/1440 px and legacy classification. Full Website unit: 730 passed / 8 unrelated public presentation assertions failed; repository lint: 5 errors / 3 warnings in unrelated files. Prior broader Backend gate remains 2,763 passed / 58 failed. Authenticated staging, real WhatsApp phone, physical devices and human language acceptance open.
FIN01 | Website + Backend | Personal Finances daily workspace | CDF/USD local-day summaries, current linked-bill obligations, expenses, cash counts, exact bill recovery and day-close safeguards; four-language responsive finance checks. | Website-only source change; Backend contract unchanged; release gate remains Partial. | Must | Partial | Restaurant engineering | 2026-10-15 | Focused Backend money/financial/daily/WhatsApp: 336/336 passed on disposable SQLite. Website focused units: 99/99 passed; build, typecheck, changed-file lint and diff checks passed. Seeded finance browser: 20/20 passed across FR/EN/LN/SW and 360/820/1440 px. Full Website units remain red: 730 passed / 8 previously red public-page failures. An older combined browser case timed out on obsolete Preparation navigation before reaching Finances; excluded from finance pass count. Prior broad Backend seller-workspace gate remains 2,763 passed / 58 failed / 21 expected skips, not rerun. Authenticated staging, real phone/tablet, physical cash/count and human language acceptance open.
RES01 | Website + Backend + WhatsApp | Personal solo Reservations workflow | Response queue, today and upcoming visits, status/date search, shared calendar, local time, copyable reference and confirmed accept/decline; preserve guest messages and idempotency. | Website-only source change. Seller DTO uses reservation reference as safe identifier and “SHIDA site or WhatsApp” source wording; Backend and WhatsApp source unchanged. | Must | Partial | Restaurant engineering | 2026-10-15 | Seeded browser 16/16 pass across FR/EN/LN/SW and 360/820/1440 px; isolated real Backend browser journey 1/1 pass; focused Backend 45 passed / 2 skipped; Website calendar focus 2/2 pass; build, typecheck, changed-file lint and diff check pass. Full Website suite remains 730 passed / 8 previously red public-page failures. Authenticated staging, real WhatsApp phone/provider, physical devices and human language acceptance open.
MENU01 | Website + Backend + WhatsApp | Personal solo Menu item setup | Offerable-first managed list; search, availability and setup filters; explicit Ready/Kitchen/Bar route, stock link, dated offering and optional photo; safe unavailable creation. | Website-only source change; current public menu and Backend order selection remain authoritative. Backend and WhatsApp source unchanged. | Must | Partial | Restaurant engineering | 2026-10-15 | Seeded production-build browser 16/16 pass, including 12 locale/width checks at 360/820/1440 px. Website focused 82/82 and Backend Menu/order/preparation focus 28/28 pass, including stale WhatsApp selection, mixed-currency rejection and preserved accepted-order routes. Build, typecheck, changed-file lint and diff check pass. Full Website units remain red: 730 passed / 8 previously red public-page failures; full ESLint 5 errors / 3 warnings outside Menu. Authenticated staging with real stock/dates, real WhatsApp provider, physical devices and human language acceptance open.
SET01 | Website + Backend + WhatsApp | Personal solo Settings | Saved state, unmet requirements, effects and confirmed intake changes; revision-safe recovery; exact owner access | Existing canonical profile, hours, intake, reservation and payment authorities retained | Must | Partial | Restaurant engineering | 2026-10-15 | Website build, typecheck and changed-file lint pass; 132 focused unit executions pass (includes existing .s3a-local duplicates); 25 production-preview browser checks pass at 360/820/1440 px in FR/EN/LN/SW. Backend intake/reservations/WhatsApp focus: 525 passed, 2 expected Organization-only skips in 1088.19s. No Backend or WhatsApp source change. Prior full-suite failures remain separate; no full-suite rerun. Staging, real WhatsApp phone/provider, physical devices and human language acceptance remain open. Website docs/restaurants-settings-2026-10-15.md and docs/evidence/restaurant-settings-2026-10-15/. No deploy, production intake, commit or push.
INT01 | Website + Backend + WhatsApp | Personal Receiving orders | Current channel status, reasons, dated periods and confirmed editing; preserve existing commitments. | Advisory exact-establishment status; canonical gates and submissions unchanged. | Must | Partial | Restaurant engineering | 2026-10-15 | Build/typecheck/changed-file lint pass. Website: 116 unit executions, 52 production-browser cases across FR/EN/LN/SW at 360/820/1440. Backend: 246 + 7 pass, fresh SQLite; head 0163, no migration. Six older combined C1-E cases fail on obsolete activity/amount expectations; full-suite red gates not rerun. Staging, real WhatsApp phone, physical devices, human language and reusable-schedule acceptance remain open. No deploy or production change.

## Launch steps
Launch steps
Ordered release work. A Pass needs evidence; this sheet does not itself authorize production release.
ID | Step | Completion evidence | Priority | Status | Owner | Date | Evidence / issue
L01 | Freeze a reviewable release commit for all three repositories. | Commit IDs and migration head recorded. | Must | Not run | SHIDA release lead |  | Local uncommitted revisions under review; complete Backend suite is red.
L02 | Resolve or explicitly triage final Backend, Website and Business suite failures. | No unexplained regression or unowned blocker. | Must | Not run | SHIDA release lead |  | Local uncommitted revisions under review; complete Backend suite is red.
L03 | Apply 0147→0148→0149 in staging with representative populated PostgreSQL data. | Migration and rollback/preservation plan reviewed. | Must | Not run | Database / Backend release engineer |  | Disposable 0147→0148→0149 rehearsal passed; staging and deployment untouched.
L04 | Upgrade every Backend API and maintenance instance. | All instances use guest/table/reservation-aware code before intake. | Must | Not run | Database / Backend release engineer |  | Disposable 0147→0148→0149 rehearsal passed; staging and deployment untouched.
L05 | Release compatible Website and Business assets together. | No mismatched contract between UI and Backend. | Must | Not run | Website + Business release engineer |  | Not run; live release step requires approval and observed evidence.
L06 | Confirm Restaurant hours, menu, stock, staff grants and owner access. | Pilot establishment setup signed off. | Must | Not run | Pilot restaurant owner + SHIDA QA |  | Not run; live release step requires approval and observed evidence.
L07 | Print and place general QR; optionally print fixed-table QRs. | Physical scan points and rotation plan verified. | Must | Not run | Pilot restaurant owner + SHIDA QA |  | Not run; live release step requires approval and observed evidence.
L08 | Decide QR auto-accept setting and test shortage behavior. | Owner knows default is off and when manual decision is needed. | Must | Not run | Pilot restaurant owner + SHIDA QA |  | Not run; live release step requires approval and observed evidence.
L09 | Run real-phone and live WhatsApp journeys in four languages. | Customer, seller and staff wording approved. | Must | Not run | Meta operations + language reviewers |  | Not run; live release step requires approval and observed evidence.
L10 | Complete one observed opening-to-close pilot day. | Physical food/stock/money/report comparison recorded. | Must | Not run | Pilot restaurant owner + SHIDA QA |  | Not run; live release step requires approval and observed evidence.
L11 | Review TLS/Origin, rate limits, privacy, retention and maintenance. | Security and operations checks have evidence. | Must | Not run | Infrastructure + security + database owners |  | Local proxy/TLS and maintenance probes passed; deployed acceptance outstanding.
L12 | Train supporters with bilingual guide and log wording issues. | Supporters can answer common questions and route incidents. | Must | Not run | Support lead |  | Staged EN/FR edit awaits every-page render; original guide unchanged.
L13 | Record founder release decision and remaining accepted limitations. | Explicit human approval after mandatory evidence. | Must | Not run | Founder / release lead |  | Pilot blocked; no production intake change or deployment authorized.
L14 | Enable intended production intake and monitor first pilot. | Rollout and monitoring owners present. | Must | Not run | Founder / release lead |  | Pilot blocked; no production intake change or deployment authorized.
L15 | Review first-day incidents, reconcile figures and update tracker. | Follow-up owner and decision for each issue. | Must | Not run | Pilot restaurant owner + SHIDA QA |  | Not run; live release step requires approval and observed evidence.

## Issues decisions
Issues and decisions
Review blocking and high items before the founder release decision.
ID | Known issue / boundary | Severity | Status | Next decision or action | Owner | Review date | Evidence / decision
I01 | Historical platform-wide suite remains red: 8076 passed / 168 failed / 1005 skipped; outside Restaurant pilot scope. | High | Open | Separate module maintenance per founder scope decision, 12 October 2026. No tests removed; shared Restaurant dependencies remain required in P01. | Backend QA | 2026-10-12 | backend_closure_final_suite.json; backend_closure_failure_causes.json; restaurant_batch_full_suite.json; restaurant_batch_intermit_ra003.xml; restaurant_batch_pg_groups.json; restaurants_pilot_release_validation_2026-10-11.md
I02 | Populated staging migration/maintenance unaccepted | Blocking | Open | Apply 0147→0148→0149 to designated staging with backup and preserved rows. | Database / release engineer | 2026-10-11 | postgres_populated_verification.txt (local rehearsal)
I03 | Inherited frontend unit/lint gates and combined workday fixture open | High | In progress | Triage 4 inherited Website unit failures and both lint gates; rebuild combined current-schema Business fixture. | Website + Business QA | 2026-10-11 | website_31_identity_disposition.json; website_units_final.txt; integrated_business_stock.txt
I04 | Live WhatsApp and FR/EN/LN/SW acceptance pending | High | Open | Personal web photos and responsive pages verified locally. Verify real-phone camera, provider storage, sign-in and native wording. Organization editor and establishment-photo removal remain follow-ups. | Meta operations + language reviewers | 2026-10-12 | Backend restaurants_photo_contract.md; Website docs/restaurants-mobile-photos.md. No live provider, device or human-language sign-off.
I05 | Observed restaurant opening-to-close journey absent | Blocking | Open | Run the documented two-guest workday with staff, stock, money, refunds and close. | Pilot restaurant owner + SHIDA QA | 2026-10-11 | Manual journeys M01-M54 Not run
I06 | Proxy shared-source fairness fixed locally; deployment open | High | In progress | Deploy both code revisions, configure same signing secret, verify shared 300 cap in staging. | Backend + Website + infrastructure | 2026-10-11 | https_guest_proxy_probe.txt; tests/test_restaurant_guest_http.py
I07 | Deployed TLS and direct-port isolation unverified | High | Open | Verify trusted forwarding, secure cookies, cache and API port isolation in staging. | Infrastructure / release engineer | 2026-10-11 | https_guest_proxy_probe.txt local only
I08 | Opening cash requires local-day attestation | Medium | Open | Train owner to record opening cash during the local day; escalate missed opening. | Pilot restaurant owner | 2026-10-11 | restaurant_daily_service.py
I09 | Alcohol display/promotion requires actual menu review | High | Open | Inspect pilot menu and WhatsApp outbound text with product policy owner. | Pilot content / policy owner | 2026-10-11 | No live pilot content reviewed
I10 | Support wording must distinguish persisted/provider/read | Medium | Open | User instructed leaving EN/FR guide staged; render every page when available, then review with support and validate live delivery wording. | Support lead + Meta operations | 2026-10-11 | support_guide_review_corrected.docx staged, original unchanged
I11 | Shared bill, recipes and cross-location reports are out of pilot scope | Info | Accepted boundary | Keep support and seller promises within implemented scope. | Product owner | 2026-10-11 | canonical restaurants_malewa.md
I12 | Founder scope decision: Restaurant pilot automated gate is separate from historical full-product suites. | Info | Accepted | Run exact scoped Backend/shared controls, PostgreSQL, frontend screens/build/type/lint. Keep live acceptance open. | Founder | 2026-10-12 | C:\NIHILOBA\Backend\docs\restaurant_pilot_test_gate.md
I13 | Selling mixed-currency quote and assigned-waiter counter sale lack canonical Backend contracts | High | Open | Define one-order CDF/USD quote and money semantics, or explicitly approve separate canonical orders; add an exact-establishment counter assignment/grant before waiter counter selling. Preserve separate payment_record authority. | Restaurant Backend / product owner | 2026-10-14 | Website docs/restaurants-selling-2026-10-14.md; Backend restaurant_order_service._calculate; restaurant_kitchen_assignment_service.grant_for

## Sources and runs
Sources and run log
Evidence paths are local handoffs. Add each final validation run below with exact commits and environment.
ID | Source | Local path / link | What it supports
S01 | Master implementation tracker | C:\Users\mabal\OneDrive\NIHILOBA\SHIDA\Development\shida_restaurants_pilot_tracker_2026-10-10.xlsx | 21/21 local implementation status; release separate
S02 | Canonical Restaurant scope | C:\NIHILOBA\Backend\docs\business_modules\restaurants_malewa.md | Restaurant policy and current module status
S03 | Guest ordering handoff | C:\NIHILOBA\nihiloba-website\docs\restaurants-rm-v11-09b2.md | Account-free guest page and release risks
S04 | Daily closing handoff | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_10b6b_daily_closing.md | Local day, cash, closing and 0145 evidence
S05 | Guest auto-accept handoff | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_guest_qr_auto_accept.md | 0146 and focused validation
S06 | Fixed tables handoff | C:\NIHILOBA\Backend\docs\restaurants_rm_v11_fixed_tables.md | 0147 and physical acceptance
S07 | Reservations handoff | C:\NIHILOBA\Backend\docs\restaurants_simple_reservations.md | 0148, account requirement, no live PostgreSQL
S08 | Business checkout handoff | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10f3_checkout.md | Service money and inherited frontend gate
S09 | Website checkout handoff | C:\NIHILOBA\nihiloba-website\docs\restaurants_rm_v11_10f3_checkout.md | Private guest money summary
S10 | Business daily operations handoff | C:\NIHILOBA\shida-business\docs\restaurants_rm_v11_10f4_daily_operations.md | Owner screens and local browser checks
S11 | Website daily operations handoff | C:\NIHILOBA\nihiloba-website\docs\restaurants_rm_v11_10f4_daily_operations.md | Personal owner screens
Validation run log — append after each test session
Date | Environment | Backend commit | Website commit | Business commit | Check IDs | Outcome | Evidence / notes
2026-10-11 | Local isolated SQLite/PostgreSQL | 75f1022727bf8bd774ace0d676df4fec0856e6d4 | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A01,A03,A05-A17 | Focused 272 pass/2 skip; PG races 26 pass | Backend evidence: backend_focused, postgres_race, postgres_money, postgres_daily, migrations, static checks
2026-10-11 | Local Website | 75f1022727bf8bd774ace0d676df4fec0856e6d4 | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A19-A22 | Build/type pass; suites/lint red | Backend/docs/evidence/restaurants_pilot_audit/website_*.txt and *_identity.json
2026-10-11 | Local Business | 75f1022727bf8bd774ace0d676df4fec0856e6d4 | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A23-A26 | Build/type pass; units/lint red | Backend/docs/evidence/restaurants_pilot_audit/business_*.txt and business_failure_identity.json
2026-10-11 | Local audit / unavailable live | 75f1022727bf8bd774ace0d676df4fec0856e6d4 | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A02,A04-A16,A18,A27-A31 | Open or blocked release gates | Backend/docs/restaurants_pilot_final_audit_2026-10-11.md
2026-10-11 | Disposable PostgreSQL 16.15; current head 0149 | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A01,A03,A30 | Populated 0147→0148→0149 and maintenance passed locally | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\postgres_populated_verification.txt; postgres_maintenance_rehearsal.txt
2026-10-11 | Website current/baseline production fixture | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A19-A22 | Current 74 pass/32 skip; baseline 74 pass/6 skip; 31 fixture-related; units 376/4 inherited | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\website_browser_final_verified.txt; website_browser_baseline_comparable.txt; website_31_identity_disposition.json; website_units_final.txt
2026-10-11 | Business local HTTPS fixture | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A23-A26 | Units 496 pass; full browser 34 pass/8 documented real-Backend skip/0 fail | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\business_units_final.txt; business_browser_current.txt
2026-10-11 | Backend four fresh SQLite shards | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A04,A18 | 7854 pass/377 fail/1005 skip; 147 additional identities vs saved 293 baseline | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\backend_baseline_comparison.json; backend_failure_identity_investigation.json
2026-10-11 | Disposable PostgreSQL 16.15, required named databases | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A06,A30 | Nine final groups 168 pass/2 expected skip; initial Stock 37/1 corrected to 38/38 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\postgres_final_groups.json; postgres_stock_worker_preparation_final.txt; postgres_maintenance_durable.txt
2026-10-11 | Current real Backend local HTTPS | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A22,A26 | Website guest 20 pass, Service 3, reservation 1; Business Service/money/daily/preparation/Stock 5 separate pass | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\integrated_website_guest_full_final.txt; integrated_website_service.txt; integrated_business_preparation_corrected.txt; integrated_business_stock.txt
2026-10-11 | Local signed HTTPS guest proxy | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A27,A28 | 12 browsers admitted; same-browser 11th limited; privacy/Origin passed | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\https_guest_proxy_probe.txt
2026-10-11 | Guide/render gate and manual acceptance | c91e47b66129bb0ccd7dbf243bc5df8f8889de7c | 1076420ad1c4b10bf31dff85a79ec35d5c132b9c | aa2e075e66696604c82da027261028660989eba5 | A29,A31,L09-L14 | Original guide unchanged; every-page render unavailable; live checks not run | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\support_guide_review_corrected.docx; docs/todo.md
2026-10-12 | Backend closure: Windows Python 3.12.7 / pytest 9.0.3, eight fresh SQLite DBs; disposable loopback PostgreSQL 16.15, durability on | 4900233b5febf610ccfdedda84032ff41cfd4638 + uncommitted app/tests diff SHA256 04b540ee17fe0d26a81d310f202d9186356f36790357bb2cb36626dfa4744fee | Website not rerun in this Backend batch | Business Dashboard not rerun in this Backend batch | A01,A03-A18,A30,I01 | Backend gate RED: 8071 passed, 173 inherited failed, 1005 skipped; original 147 additions closed; Restaurant focused 276/2; PostgreSQL 168/2; head 0150 | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\backend_closure_final_suite.json; backend_closure_failed_nodes.txt; backend_closure_failure_causes.json; backend_closure_pg_groups.json; backend_closure_restaurant_focused.xml; backend_closure_populated_0149_to_0150.json
2026-10-12 | Backend Restaurant closure: eight fresh SQLite databases; disposable PostgreSQL 16 at head 0150 | d6c5fbbe6aa541d651e266f77fc4b99e3b81efb2 + uncommitted app/tests diff SHA256 a50adbd6bde7ae24384788dedf4c69890bd8ab1a4a4c103291b9dcfbc0ff765c | Website not rerun in this Backend batch | Business Dashboard not rerun in this Backend batch | A01,A04-A17,I01 | Backend gate RED: 8076 pass/168 fail/1005 skip; six Restaurant IDs resolved; one new intermittent shared security ID; nine PG groups 168 pass/0 fail/2 skip | C:\NIHILOBA\Backend\docs\evidence\restaurants_pilot_release\restaurant_batch_full_suite.json; restaurant_batch_pg_groups.json; restaurant_six_before.xml; restaurant_six_after.xml; restaurant_three_files.xml; restaurant_related.xml; restaurant_batch_intermit_ra003.xml; restaurant_batch_tracker_readback.txt
2026-10-12 | Disposable SQLite/PostgreSQL and local production-build browsers; no live services | 9bb7b2d024f2c10e0a9167ac8ebdb99cb65fec2c | 8c7f29351ca79f15169cf717279a9da586eda7e3 | be7e6abe99f37cdd05029f48d574eba8956e93f3 | P01 onward; I12; historical A04 remains Fail | Restaurant pilot automated gate: Pass; historical full suites not rerun | C:\NIHILOBA\Backend\docs\evidence\restaurant_pilot_gate\results.json
2026-10-12 | Fresh isolated SQLite; mocked Meta boundary | f9768b5b2e710f8d03482407e4a200d0c2c4cdd6 + uncommitted WhatsApp fixes | Not changed | Not changed | A29 / I04 | Scoped backend checks; live gate stays blocked | Backend/docs/evidence/restaurants_whatsapp_2026_10_12/manifest.json; full handoff: restaurants_whatsapp_journey_2026-10-12.md. No deploy or intake change.
2026-10-12 | Optional Restaurant photos; isolated SQLite and durable PostgreSQL | Backend local working tree; additive head 0151 | Personal photo editor and responsive customer pages implemented locally. Website docs/restaurants-mobile-photos.md records checks and screenshots. | Organization photo editor follow-up pending at business.nihiloba.com. | A29 / A30 / I04 | Local validation only; live gate remains blocked | Backend/docs/restaurants_photo_contract.md; restaurants_photo_implementation.md; Website/docs/restaurants-mobile-photos.md and evidence/restaurants-mobile-photos/validation.json.
2026-10-13 | Restaurant management redesign | Backend local working tree; no migration | Personal seller shell / Orders entry / contextual photos | Business Restaurant navigation only | MGT01 | Local implementation and validation; release remains gated | Website/docs/restaurants-management-2026-10-13.md
2026-10-14 | Shared calendar batch 1; isolated Backend and local responsive browser checks | Backend local working tree; sole Alembic head 0156; no migration | Website Restaurant seller calendar/customer date picker locally connected; Services and Apartment adapters unmounted | Business Restaurant seller calendar locally connected; Services adapter unmounted | CAL01; M55-M56 | Focused local checks passed; full Services browser gate, staging, devices and live acceptance remain open | C:\NIHILOBA\Backend\docs\shared_calendar_batch1.md
2026-10-13 | Website local production HTTPS + disposable Backend SQLite and isolated public fixtures | Backend unchanged; local fixture only | 93d5701131b3ac17688396e8d58de5f276d8aa3c + uncommitted customer redesign | Business unchanged | CUX01; A19-A22 (local subset) | Local implementation and tested customer journeys; release acceptance still open | Website docs/restaurants-customer-redesign.md; screenshot directory docs/evidence/restaurants-customer-redesign/. No physical device or live provider acceptance.
2026-10-14 | Local Website and Business production builds; disposable SQLite Backend, production HTTPS browser and mocked responsive fixtures | Backend policy unchanged; concurrent migration head 0156 | Website Restaurant workspace changes, uncommitted | Business Restaurant workspace changes, uncommitted; concurrent Services preserved | MGT01; P01/P02/P05/P06/P07/P08/P09/P12 | Local implementation and journey checks passed; scoped Backend gate Fail: 2763 passed / 58 failed / 21 skipped (0 unexpected skips). Release remains gated. | Website docs/restaurants-seller-workspace-2026-10-14.md; .s3a-local/restaurant-workspace-gate-2026-10-14/summary.json. No deploy, intake, commit or push.
2026-10-14 | Restaurant Selling / POS local correction; seeded responsive browser journeys | Backend canonical orders retained; optional sanitized POS photo field only; red scoped gate separate | Website Selling menu/basket and order reference; 12/12 FR/EN/LN/SW responsive screenshots; focused tests and typecheck pass | Business Selling parity and assigned Service payment grant preserved; 12/12 responsive screenshots; focused tests and typecheck pass | MGT01; P07/P08; I13 | Partial: mixed-currency quote and waiter counter permission require Backend contract; local Backend test teardown failed; staging and physical workday open | Website docs/restaurants-selling-2026-10-14.md and docs/evidence/restaurant-selling-2026-10-14/. No deploy, intake, commit or push.
2026-10-14 | Personal Restaurant Orders queue; local production Website and seeded responsive journeys | Backend order states/actions inspected; canonical Kitchen/Bar, handover, stock and payment unchanged; existing red gate separate | Website Orders page and localized copy, uncommitted; 308 scoped Restaurant tests (135 focused subset), build, typecheck and lint pass | Business unchanged | MGT01; P05/P07/P09/P10/P12 | Partial: 44 seeded production-server browser checks pass; physical devices, live authenticated journey and red Backend gate remain open | Website docs/restaurants-orders-2026-10-14.md and docs/evidence/restaurant-orders-2026-10-14/. No deploy, production intake, commit or push.
2026-10-14 | Solo Restaurant/Malewa Orders, preparation and WhatsApp; disposable local SQLite and seeded Website browser | Uncommitted Backend working tree at local head 0158 | Uncommitted Website working tree; production build | Organization worker routes retained; Business UI unchanged | SOLO01; M56/M57 remain Not run | Partial: Affected Backend suite: 371 passed; assisted ready-to-serve: 2 passed; migration: 2 passed; automatic acceptance, assisted orders and tables: 71 passed. Real phone, authenticated staging, physical devices and human language acceptance remain open. | Website docs/restaurants-solo-orders-2026-10-14.md; Backend tests/test_restaurant_ready_to_serve_migration.py. No deploy, production intake, commit or push.
2026-10-15 | Personal Restaurant Stock; disposable SQLite and seeded Chrome at 360/820/1440 px | Backend local head 0159; no deployment | Website Stock list/actions/history, uncommitted | Business workspace unchanged; Organization worker grants retained | STOCK01; M58 Not run | Partial: focused Backend/WhatsApp and stock worker checks passed (70 initial, 34 final stock, 33 worker, 348 preparation/assisted/WhatsApp, 22 final wording/migration). Website build/typecheck, changed-file lint, 91 focused units and 14 seeded Chrome checks passed. Full Website unit/lint and prior broad Backend gate remain red separately; live acceptance open. | Website docs/restaurants-stock-2026-10-15.md and docs/evidence/restaurant-stock-2026-10-15/ captures. No deploy, production intake, commit or push.
2026-10-15 | Personal Restaurant & Malewa Finances; disposable Backend SQLite and seeded production-browser finance fixtures | Backend source unchanged; local head 0159; focused money/financial/daily/WhatsApp tests 336/336 pass | Website Finances daily workspace, uncommitted; build/typecheck/lint and 99 focused units pass | Business unchanged; Organization grants preserved | FIN01; M59 Not run | Partial: 20/20 finance browser checks pass; full Website units 730 passed / 8 failed; prior broad Backend gate red and not rerun. Older combined browser case timed out on obsolete Preparation navigation; live acceptance open. | Website docs/restaurants-finances-2026-10-15.md and docs/evidence/restaurant-finances-2026-10-15/. No deploy, production intake, Backend source edit, commit or push.
2026-10-15 | Personal Restaurant & Malewa Reservations and Menu; local Website production browsers and disposable Backend focus | Backend source unchanged at local head 0159; Reservations focus 45 pass / 2 skip and isolated journey 1/1; Menu/order/preparation focus 28/28 pass | Website-only Reservations and Menu page changes; Reservations browser 16/16 and calendar focus 2/2; Menu browser 16/16 and focused units 82/82; build/typecheck/changed-file lint/diff pass | Business and Organization grants unchanged; WhatsApp source unchanged | RES01 + MENU01 Partial; M60 + M61 Not run | Release Partial: full Website 730 pass / 8 fail; full lint 5 errors / 3 warnings outside Menu; prior broad Backend gate red. Authenticated staging, real phone/provider, physical devices and human FR/EN/LN/SW acceptance open. | Website docs/restaurants-reservations-2026-10-15.md, docs/restaurants-menu-2026-10-15.md and docs/evidence/restaurant-personal-menu-2026-10-15/tracker-update.md. No deploy, production intake, Backend/WhatsApp source edit, commit or push in these batches.
2026-10-15 | Personal Restaurant and Malewa Settings; synthetic production-preview browsers and disposable Backend SQLite | Backend source unchanged; 525 passed / 2 expected skips | Website local uncommitted Settings; 132 unit executions and 25 browser cases pass | Business and WhatsApp source unchanged | SET01 Partial | Staging, real WhatsApp phone/provider, physical devices and human FR/EN/LN/SW acceptance remain open. Prior full-suite failures not rerun. | Website docs/restaurants-settings-2026-10-15.md and docs/evidence/restaurant-settings-2026-10-15/. No deploy, production intake, commit or push.
2026-10-15 | Receiving orders; local production browser + disposable SQLite | 253 focused Backend passes; head 0163; no migration | 52 browser cases and 116 Website unit executions; build/typecheck/lint pass | Business unchanged; WhatsApp draft/recheck retained | INT01 Partial | Live/staging/device/human languages and reusable schedule remain open; older broad red gates unchanged. | C:/NIHILOBA/nihiloba-website/docs/restaurants-receiving-2026-10-15.md